**2018 new week plan for my project**

Student: Jerry / Jie Sun

Tutor: Dr. Glavin, Frank

The total task for the next three weeks:

1. **Finish the first draft of my thesis, at lease complete the frame until only just need to be revised.**

12/01/2018 --- 18/01/2018 (first week)

|  |  |
| --- | --- |
| Week Plan |  |
|  | 1. Finish the contents of the introduce chapter and the Gyroscope chapter |
| 1. Organize the picture format and some references |
| Summary |  |
|  | 1. Finished the first draft |
| 1. Finished |

19/01/2018 ---25/01/2018 (Second week)

|  |  |
| --- | --- |
| Week Plan |  |
|  | 1. Giving an introduction, several words, for the last chapter, My glow sticks |
| 1. Finding a 3D tool to draw a handle for the glow sticks for the description of it new functions |
| Summary |  |
|  | 1. 20% finished |
| 1. 0% finished |

26/01/2018 ---01/02/2018 (Third week)

|  |  |
| --- | --- |
| Week Plan |  |
|  | 1. Finish the last chapter, glow stick part |
| 1. Go back to review or check all parts information and adjust it |
| Summary |  |
|  | 1. 0% finished |
| 1. 0% finished |

**//new plan from 01/02/2018 is a month plan.**

**//go back to China between 09/02/2018 – 20/02/2018,but no effect for the process**

01/02/2018 ---01/03/2018 ()

|  |  |
| --- | --- |
| Week Plan  (purpose) |  |
|  | 1. Finish the four chapter, my own design    1. Write the introduction and describe the concept of the idea of my design.    2. Drawing a picture to help the readers to understand the principle of my design    3. Collect the data from those three postures of action, Parallel, Perpendicular shaking to body and ring shaking. And creating an APP to calculate the result of action recognition, such as 1 meaning parallel shaking to the body and to show the result.    4. Creating some algorithms to avoid the disturbance signals.    5. Verify the feasibility of those algorithms, such as filtering algorithm.    6. Summarize the result and show in the table. |
| 1. Finish the introduction part and give some words for generalizing the entire title. |
| Summary |  |
|  |  |
|  |